## Dashboard
Placement Prep Tracker — Keshav Mittal
DTU IT ¦ 3rd Year → 4th Year ¦ Target: SWE @ Mid-size Product Companies
Placement window: | < 1 month — every day counts. Track daily, not weekly.
AREA | DONE | TOTAL | % COMPLETE | PRIORITY | STATUS
DSA (Blind 75) | 0 | 75 | 0% | P1 — Highest | Needs Attention
Project (GymKhanna) | 0 | 17 | 0% | P1 — Finish, don't expand | Needs Attention
SQL Practice | 0 | 11 | 0% | P1 — New & cheap | Needs Attention
LLD Patterns | 0 | 10 | 0% | P2 — Pattern only | Needs Attention
Core Subjects Revision | 0 | 25 | 0% | P3 — Revise, don't relearn | Needs Attention
Resume & Behavioral | 0 | 15 | 0% | P2 — Do early | Needs Attention
OVERALL COMPLETION |  |  | 0%
3-WEEK SEQUENCE
Week 1 | Pick Blind 75, start daily solving. Finish GymKhanna's remaining 40%. Start SQL (1-2 hrs/day).
Week 2 | Continue Blind 75 + pull thin topics from LC150. Polish GymKhanna, prep to explain every decision. Skim 5 LLD problems. Write behavioral stories.
Week 3 | Mock interviews, timed DSA practice. Resume deep-dive prep. Light revision: OOP/OS/CN/DBMS — explain-aloud level only.
Note: OS/CN are revision-only this cycle — don't go deep, redirect that time to SQL + LLD pattern recognition + resume defense.

## DSA Tracker
DSA Tracker — Blind 75
Since CP-style topics (graphs, DP, segment trees, monotonic deques) are already strong, this list is mostly coverage-check + speed. Mark gaps and pull matching topics from LC150 if needed.
# | Problem / Topic | Pattern | Difficulty | Status | Notes / Gap?
1 | Two Sum | Array / Hashing | Easy | To Do
2 | Contains Duplicate | Array / Hashing | Easy | To Do
3 | Product of Array Except Self | Array / Hashing | Medium | To Do
4 | Maximum Subarray (Kadane's) | Array / Hashing | Medium | To Do
5 | Maximum Product Subarray | Array / Hashing | Medium | To Do
6 | Find Minimum in Rotated Sorted Array | Binary Search | Medium | To Do
7 | Search in Rotated Sorted Array | Binary Search | Medium | To Do
8 | 3Sum | Array / Two Pointers | Medium | To Do
9 | Container With Most Water | Two Pointers | Medium | To Do
10 | Sum of Two Integers (bit trick) | Bit Manipulation | Medium | To Do
11 | Number of 1 Bits | Bit Manipulation | Easy | To Do
12 | Counting Bits | Bit Manipulation | Easy | To Do
13 | Missing Number | Bit Manipulation | Easy | To Do
14 | Reverse Bits | Bit Manipulation | Easy | To Do
15 | Climbing Stairs | Dynamic Programming | Easy | To Do
16 | Coin Change | Dynamic Programming | Medium | To Do
17 | Longest Increasing Subsequence | Dynamic Programming | Medium | To Do
18 | Longest Common Subsequence | Dynamic Programming | Medium | To Do
19 | Word Break | Dynamic Programming | Medium | To Do
20 | Combination Sum IV | Dynamic Programming | Medium | To Do
21 | House Robber | Dynamic Programming | Medium | To Do
22 | House Robber II | Dynamic Programming | Medium | To Do
23 | Decode Ways | Dynamic Programming | Medium | To Do
24 | Unique Paths | Dynamic Programming | Medium | To Do
25 | Jump Game | Dynamic Programming / Greedy | Medium | To Do
26 | Clone Graph | Graph | Medium | To Do
27 | Course Schedule | Graph (Topo Sort) | Medium | To Do
28 | Pacific Atlantic Water Flow | Graph (DFS/BFS) | Medium | To Do
29 | Number of Islands | Graph (DFS/BFS) | Medium | To Do
30 | Longest Consecutive Sequence | Graph / Union-Find | Medium | To Do
31 | Alien Dictionary | Graph (Topo Sort) | Hard | To Do
32 | Graph Valid Tree | Graph / Union-Find | Medium | To Do
33 | Number of Connected Components | Graph / Union-Find | Medium | To Do
34 | Insert Interval | Intervals | Medium | To Do
35 | Merge Intervals | Intervals | Medium | To Do
36 | Non-overlapping Intervals | Intervals | Medium | To Do
37 | Meeting Rooms | Intervals | Easy | To Do
38 | Meeting Rooms II | Intervals | Medium | To Do
39 | Reverse a Linked List | Linked List | Easy | To Do
40 | Detect Cycle in Linked List | Linked List | Easy | To Do
41 | Merge Two Sorted Lists | Linked List | Easy | To Do
42 | Merge K Sorted Lists | Linked List / Heap | Hard | To Do
43 | Remove Nth Node From End of List | Linked List | Medium | To Do
44 | Reorder List | Linked List | Medium | To Do
45 | Set Matrix Zeroes | Matrix | Medium | To Do
46 | Spiral Matrix | Matrix | Medium | To Do
47 | Rotate Image | Matrix | Medium | To Do
48 | Word Search | Matrix / Backtracking | Medium | To Do
49 | Longest Substring Without Repeating Characters | String | Medium | To Do
50 | Longest Repeating Character Replacement | String / Sliding Window | Medium | To Do
51 | Minimum Window Substring | String / Sliding Window | Hard | To Do
52 | Valid Anagram | String | Easy | To Do
53 | Group Anagrams | String / Hashing | Medium | To Do
54 | Valid Parentheses | Stack | Easy | To Do
55 | Valid Palindrome | String / Two Pointers | Easy | To Do
56 | Longest Palindromic Substring | String / DP | Medium | To Do
57 | Palindromic Substrings | String / DP | Medium | To Do
58 | Encode and Decode Strings | String | Medium | To Do
59 | Maximum Depth of Binary Tree | Tree | Easy | To Do
60 | Same Tree | Tree | Easy | To Do
61 | Invert/Flip Binary Tree | Tree | Easy | To Do
62 | Binary Tree Maximum Path Sum | Tree | Hard | To Do
63 | Binary Tree Level Order Traversal | Tree / BFS | Medium | To Do
64 | Serialize and Deserialize Binary Tree | Tree | Hard | To Do
65 | Subtree of Another Tree | Tree | Easy | To Do
66 | Construct Binary Tree from Preorder/Inorder | Tree | Medium | To Do
67 | Validate Binary Search Tree | Tree (BST) | Medium | To Do
68 | Kth Smallest Element in a BST | Tree (BST) | Medium | To Do
69 | Lowest Common Ancestor of BST | Tree (BST) | Medium | To Do
70 | Implement Trie (Prefix Tree) | Trie | Medium | To Do
71 | Add and Search Word | Trie | Medium | To Do
72 | Word Search II | Trie / Backtracking | Hard | To Do
73 | Top K Frequent Elements | Heap | Medium | To Do
74 | Find Median from Data Stream | Heap | Hard | To Do
75 | Combination Sum | Backtracking | Medium | To Do
76 | Permutations | Backtracking | Medium | To Do
77 | Subsets | Backtracking | Medium | To Do
Total problems: | 77
Done: | 0
% Complete: | 0%

## Project Tracker
Project Tracker — GymKhanna (MERN Fitness Tracker)
Currently ~60% done. Goal: finish core features only this week — no scope creep. Be ready to explain every decision.
# | Feature / Task | Layer | Why it matters in interview | Status | Notes
1 | Workout logging — CRUD | Backend (API) | Core feature; expect 'walk me through this flow' question | To Do
2 | Workout logging — UI | Frontend | Demonstrates React state/forms handling | To Do
3 | Progressive overload calc logic | Backend (Logic) | Good 'explain your algorithm/logic' talking point | To Do
4 | PR (personal record) detection | Backend (Logic) | Shows you can design business logic, not just CRUD | To Do
5 | Streak tracking | Backend (Logic) | Date/time edge cases — good debugging story | To Do
6 | Weight tracking | Full stack | Simple CRUD — confirm it's fully working | To Do
7 | Water intake tracking | Full stack | Simple CRUD — confirm it's fully working | To Do
8 | MongoDB schema design | Database | Be ready to explain why this schema, relations/embedding choice | To Do
9 | Auth (login/signup) | Backend (Security) | Common interview Q: how is auth handled, JWT vs sessions | To Do
10 | Input validation | Backend | Shows attention to robustness, not just happy path | To Do
11 | Error handling middleware | Backend | Shows maturity beyond a tutorial-level app | To Do
12 | Responsive UI pass | Frontend | Polish — don't over-invest, but should look presentable | To Do
13 | Deploy (e.g. Render/Vercel) | DevOps | Live link > localhost screenshot in interviews | To Do
14 | README with setup + architecture | Docs | Interviewers do check this — keep it clean | To Do
15 | Daily GitHub commit habit | Process | Shows consistency — keep streak alive through prep | To Do
16 | Mock 'explain this project' run-through | Interview Prep | Practice explaining out loud, not just building | To Do
17 | Identify 1-2 'what would you improve at scale' answers | Interview Prep | Very commonly asked follow-up | To Do

## LLD Tracker
LLD Tracker — Pattern Recognition Only
Goal is NOT mastery (no time for that). Goal is: recognize the shape of the question, talk through classes/relationships, cite a relevant OOP principle.
# | Problem | Core OOP Concept Tested | Time-box | Status | Notes
1 | Design a Parking Lot | Inheritance, interfaces, strategy pattern | 45 min | To Do
2 | Design Splitwise (expense sharing) | Composition, balancing algorithm logic | 45 min | To Do
3 | Design Tic-Tac-Toe / Board game | State management, encapsulation | 30 min | To Do
4 | Design a Library Management System | Associations, single responsibility | 30 min | To Do
5 | Design an Elevator System | State machine, concurrency basics | 30 min | To Do
6 | Design a Vending Machine | State pattern, encapsulation | 30 min | To Do
7 | Design a Rate Limiter (basic) | Strategy pattern, simple system design overlap | 30 min | To Do
8 | Design a URL Shortener (basic) | Hashing logic, simple system design overlap | 30 min | To Do
9 | SOLID Principles — explain each with example | Foundational — must be fluent | 30 min | To Do
10 | Composition vs Inheritance — explain with example | Foundational — commonly asked directly | 20 min | To Do

## Core Subjects
Core Subjects — Revision + SQL Practice
OOP/OS/CN/DBMS = revision only, 'explain clearly out loud' depth. SQL = new, prioritize this. Don't re-learn — confirm fluency.
# | Topic | Subject | Depth Needed | Status | Notes
1 | 4 pillars (Encapsulation, Abstraction, Inheritance, Polymorphism) with examples | OOP | Explain-aloud | To Do
2 | Compile-time vs runtime polymorphism | OOP | Explain-aloud | To Do
3 | Constructors, destructors, virtual functions | OOP | Explain-aloud | To Do
4 | Diamond problem / multiple inheritance issues | OOP | Explain-aloud | To Do
5 | Process vs Thread | OS | Explain-aloud | To Do
6 | Deadlock — causes + prevention | OS | Explain-aloud | To Do
7 | Scheduling algorithms (overview only) | OS | Explain-aloud | To Do
8 | Paging vs Segmentation (overview) | OS | Explain-aloud | To Do
9 | Mutex vs Semaphore | OS | Explain-aloud | To Do
10 | Virtual memory — basic concept | OS | Explain-aloud | To Do
11 | TCP vs UDP | CN | Explain-aloud | To Do
12 | OSI model layers (overview) | CN | Explain-aloud | To Do
13 | DNS resolution flow (overview) | CN | Explain-aloud | To Do
14 | HTTP vs HTTPS, status codes basics | CN | Explain-aloud | To Do
15 | 3-way handshake | CN | Explain-aloud | To Do
16 | ACID properties | DBMS | Explain-aloud | To Do
17 | Normalization (1NF-3NF) with example | DBMS | Explain-aloud | To Do
18 | Indexing — what & why | DBMS | Explain-aloud | To Do
19 | Primary key vs Foreign key vs Unique key | DBMS | Explain-aloud | To Do
20 | Joins — conceptual (Inner/Left/Right/Full) | DBMS | Explain-aloud | To Do
21 | SQL vs NoSQL — when to use which | DBMS | Explain-aloud | To Do
22 | Transactions & isolation levels (overview) | DBMS | Explain-aloud | To Do
23 | Why MongoDB for GymKhanna — be ready to defend | DBMS | Project-specific | To Do
24 | OOP applied: map GymKhanna design to OOP principles | OOP | Project-specific | To Do
25 | Networking basics applied to MERN (REST, CORS, ports) | CN | Project-specific | To Do
SQL PRACTICE (NEW — HIGH PRIORITY)
1 | Basic SELECT, WHERE, ORDER BY | SQL | Hands-on | To Do
2 | GROUP BY + HAVING | SQL | Hands-on | To Do
3 | INNER / LEFT / RIGHT / FULL JOIN — write queries | SQL | Hands-on | To Do
4 | Subqueries (nested SELECT) | SQL | Hands-on | To Do
5 | Aggregate functions (COUNT, SUM, AVG, MIN, MAX) | SQL | Hands-on | To Do
6 | Window functions (RANK, ROW_NUMBER) — if time permits | SQL | Hands-on (stretch) | To Do
7 | UPDATE / DELETE with conditions | SQL | Hands-on | To Do
8 | Self joins | SQL | Hands-on | To Do
9 | CASE WHEN logic in queries | SQL | Hands-on | To Do
10 | Practice 10-15 SQL problems (LeetCode SQL / HackerRank) | SQL | Hands-on | To Do

## Resume & Behavioral
Resume Deep-Dive & Behavioral Prep
Assume every resume line gets questioned. Prep stories using situation-action-result structure.
# | Item | Type | Status | Key Points / Story Notes
1 | GymKhanna — why MERN, why this schema | Resume Defense | To Do
2 | GymKhanna — PR detection / streak logic walk-through | Resume Defense | To Do
3 | GymKhanna — what would you change at scale | Resume Defense | To Do
4 | Take-Note — Redis rate limiting explanation | Resume Defense | To Do
5 | Take-Note — CORS / ES module issues you debugged | Resume Defense | To Do
6 | Huffman Compressor — algorithm explanation | Resume Defense | To Do
7 | Toughest bug you've debugged (any project) | Resume Defense | To Do
8 | Engifest — Head of PR: leadership story | Behavioral | To Do
9 | Engifest — conflict resolution story | Behavioral | To Do
10 | A time you failed / made a mistake | Behavioral | To Do
11 | A time you handled ambiguity | Behavioral | To Do
12 | Why this company / role (tailor per company) | Behavioral | To Do
13 | Strengths & weaknesses — have real examples ready | Behavioral | To Do
14 | Questions to ask the interviewer | Behavioral | To Do
15 | Resume — read it cold, anticipate every question | Resume Defense | To Do

## Daily Log
Daily Log
Fill this every evening — 5 min. Forces honest tracking against the <1 month window.
Date | DSA (# solved) | GymKhanna progress | SQL / LLD / Core | Hours studied | Reflection / blocker